## Client
Task Number | Description | Developer | Status | Questions
1 | LogInActivity created - this includes register tab and log in tab | James | complete
2 | LogInActivity Log in functionality - allows user to log in using username and password, includes the checkboxes and their functionality | James | complete | need to add facebook and twitter buttons
3 | LogInActivity Register functionality - all the editTexts and scrolldown of agents for the client to choose from and create a new user on the parse end, does not log in but opens up the Log In tab for the user to try to log in | James | complete
4 | NavigationDrawerFragment - develop the list, excludes dropdown list/meet the interns listItem | Navneet | Complete
5 | NavigationDrawerFragment - create Meet the intern item as well as the dropdown that works in the NavigationDrawer | Navneet | Complete
6 | SplashScreen - opens when logging in, should not be shown otherwise. Opens in login screen, fragment which transitions to login sure | Levi | Complete
7 | MyAgentFragment - Implement the textViews and button the Imagebuttons on the fragment with the background invisible, ImageView at the Top with the Agent photo ( needs to be implemented so use a holder for now ) and a floating button | Evan | Complete | might need some help using FAB
8 | MyAgentFragment - Implement the floating button to email the client | Evan | Changed
9 | MyAgentFragment - Implement the intent to call the agent and direct you to the agent address | Evan | Complete
10 | MyAgentFragment - Implement the button to schedule a meeting with your agent | James |  | agent selection can be opened multiple times
11 | MyPoliciesFragment - Develop the two types of cards, one for policies with upload, and the other for policies without uploads | Navneet | Complete
12 | MyPoliciesFragment - edit Button is part of the card but looks like floating button with the edit pencil in it and description and cost, ( if picture, the description is over the image ) | Navneet | Complete | Need to do overlapping of components.
13 | MyPoliciesFragment - a plus button on the app bar that will open up the blank PolicyScreenFragment | Navneet | Complete | If clicked pass in bundle ("ISNEW", true)
14 | MyPoliciesFragment - clicks on the card will open PolicyScreenFragment in its uneditable mode | Navneet | Complete | Set Value of currentPolicy in Singleton on policy selected
15 | MyPoliciesFragment - clicks on the edit button opens the PolicyScreenFragment in its editable mode | Navneet | Complete | If EditPolicy is selected setValue of currentPolicy in singleton and pass bundle with ("ISEDIT", true)
16 | PolicyScreenFragment - have all the editTexts, labels, spinners, and listViews | Levi | Complete.
17 | PolicyScreenFragment - design the two upload cards, one that has a editText,delete X, and ImageButton for the image. The other with just a textView and Image | Levi | Complete
18 | PolicyScreenFragment - make editable mode, editTexts enabled to edit, plus button, upload listViewItem with delete button and editTexts, and a save button on app bar | Levi | Complete.
19 | PolicyScreenFragment - make uneditable mode, editTexts disabled to edit, no plus button, upload listViewItem with textView | Levi | Complete.
20 | PolicyScreenFragment - open editable mode blank | Levi | Complete.
21 | PolicyScreenFragment - open uneditable and editable mode with infromation filled in | Levi | Complete.
22 | MyClaimsFragment - Develop the two cards one for claims with uploads and the other for claims without uploads | James | Complete
23 | MyClaimsFragment - Add the Floating Action Button which will open the ClaimScreenFragment in a blank editable mode | James | Complete | If clicked pass in bundle ("ISNEW", true)
24 | MyClaimsFragment - if card is clicked on it opens the uneditable mode with the information filled in. | James | Complete | Set value of of CurrentClaim in Singleton on claim selected
25 | ClaimScreenFragment - Create an editable mode with the editTexts enabled to edit, plus button visible, and cards with editTexts, imageButton, and Delete Button | Levi | Complete
26 | ClaimScreenFragment - Create an uneditable mode with the editTexts disabled to edit, no plus button visible, and listViewITems with the imageView and editTexts | Levi | Complete
27 | ClaimScreenFragment - has a save button on app bar if opened in editable mode | Levi | Complete
28 | SettingsFragment - set up the textviews, imageview, and button | James | Complete
29 | SettingsFragment - set the name, address, phone, email with the users information | James | complete
30 | SettingsFragment - Log out button logs out of parse and kicks the users back to the LogInActivity | James | complete
31 | SettingsFragment - Display the current version of the app | James | complete
32 | NavigationDrawerFragment - Find an Agent which opens up the google maps showing all results of "American Family Agents" search - might need to use a url that has that search updated with current location | Navneet | Complete
33 | Settings Page crashes if not all fields are filled out when creating new User. Create Validation or check to see if values are null before setting them in settings | James | Complete
34 | MeetTheInternFragments - develop your own fragment | Evan, James, Levi, Navneet | Empty Fragments made for all four interns; Levi - Completed
35 | Product design - image finding, design, clean up of xml | Evan | Complete
36 | Presentation development | Evan | Complete
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Agent
Task Number | Description | Developer | Status | Questions
1 | Policy Upload - when photos are selected it will only put the first one in
2 | When a Policy is added through clients tab it does not show up on the list, it is on parse but the list is not updated, maybe just can't show more than 1
3 | when making a new policy it goes to the main screen it shouldn't, plus the whole reopening the fragment with a new fragment is weird, why not just have the uploads fragment there in the first place
4 | When clicking the save button it should take you back to the client list, and might not need the toast
5 | Claims Information Screens, does not show its uploads
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49